## Sheet1
EMILY'S PET SITTING TIME LOG BOOK
date | activity | HH:MM | minutes
2019-05-20 | Website rough outline discussion | 0:30 | 30
2019-05-21 | Project setup Basic mobile page template setup Moblie sliding menu sidebar | 4:30 | 270
2019-05-22 | Notes Contact page setup Time log setup Contact page testing Contact page error messages Contact page layout | 5:20 | 320
2019-05-23 | Notes About page basic setup Services page basic setup Photos page basic setup Testimonalis page basic setup local host connection Admin login page setup About_Update page setup About_Update form working | 6:15 | 375
2019-05-24 | About_Update page About Page Database work Service_Update page | 4:00 | 240
0
0
0
0
0
Total minutes:
1235